## Calendar
Test Schedule
Pom's | 2014-03-10 | 2014-03-11 | 2014-03-12 | 2014-03-13 | 2014-03-14
1 | Sprint Kick Off | Review Model | Test Session | Test Session | Sprint Close
2
3
4 | Test Modeling | Sessions and Charters | Test Session | Test Session | Retrospective
5
6
7 |  | Test Session | Test Session | Test Session | Cleanup
8
9
10 |  | Test Session | Test Session | Test Session
11
12
5 | hrs

## Dashboard
Start | 2014-03-11
Testing Dashboard | Priority | Effort | Risk | Coverage | Quality | Critical Defects | Defects | OTD's | Comments
Area
Area Name | 0 | Start | 0 | 2 - Common Cases: all functions touched; common & critical tests executed | Good | 0 | 0
|  | None |  | 0 - We have no good information about this area | Ugly
|  | None |  | 0 - We have no good information about this area | Ugly
|  | None |  | 0 - We have no good information about this area | Ugly
|  | None |  | 0 - We have no good information about this area | Ugly
|  | None |  | 0 - We have no good information about this area | Ugly
|  | None |  | 0 - We have no good information about this area | Ugly
|  | None |  | 0 - We have no good information about this area | Ugly
|  | None |  | 0 - We have no good information about this area | Ugly
|  | None |  | 0 - We have no good information about this area | Ugly
http://katrinatester.blogspot.com/2014/03/reporting-session-based-testing.html
http://www.satisfice.com/presentations/dashboard.pdf
http://media.wix.com/ugd//c47e45_43a2d6b64e59a0b6d8ebf2c0f44001e2.pdf

## Dashboard Legend
Product Area | 15-30 areas (keep it simple) n Avoid sub-areas: they’re confusing. n Areas should have roughly equal value. n Areas together should be inclusive of everything reasonably testable. n “Product areas” can include tasks or risks- but put them at the end. n Minimize overlap between areas. n Areas must "make sense" to your clients, or they won’t use the board.
Priority
Effort | Description
None | Not testing; not planning to test.
Maintenance | Regression or spot testing only; maintaining coverage.
Low | Focused testing effort; increasing coverage.
High | No testing yet, but expect to start soon.
Pause | Temporarily ceased testing, though area is testable.
Blocked | Can’t effectively test, due to blocking problem.
Release | Going through final tests and signoff procedure.
Risk | ACC
Coverage
0 - We have no good information about this area |  | No testing, or very little testing
1 - Sanity Check: major functions & simple data |  | All specification based tests (100% traceability) complete for this area
1+ - More than sanity, but many functions not tested |  | All initially identified regression tests complete for this area
2 - Common Cases: all functions touched; common & critical tests executed |  | All follow up charters complete for this area
2+ - Some data, state, or error coverage beyond level 2 |  | Subjective call of tester responsible for area based on tester's understanding of performance, reliability, usability, (and other “ilities”) for this area indicating this area of the product will work under realistic usage
3 - Corner Cases: strong data, state, error, or stress testing |  | Subjective call of tester responsible for area where the tester is basically saying, "if there were a bad bug in this area, we would probably know about it."
n Color green if coverage level is acceptable for ship, otherwise color black.
n Level 1 and 2 focus on functional requirements and capabilities: can this product work at all?
n Level 2 may span 50%-90% code coverage.
n Level 2+ and 3 focus on information to judge performance, reliability, compatibility, and other “ilities”: will this product work under realistic usage?
n Level 3 or 3+ implies “if there were a bad bug in this area, we would probably know about it.”
As a general rule, a coverage value of 2 is normally sufficient for any area.
Quality
Good | “We know of no problems in this area that threaten to stop ship or interrupt testing, nor do we have any definite suspicions about any.”
Bad | “We know of problems that are possible showstoppers, or we suspect that there are important problems not yet discovered.”
Ugly | “We know of problems in this area that definitely stop ship or interrupt testing.”
OTD's | OTD Number of defects related to testing the area. Red indicates show stopping defect.
Comments
Reasons for pausing, or delayed start.
Nature of blocking problems.
Why area is unstaffed.

## Area 1
Area: | Area Name
Priority:
Risk:
Effort: | Start |  |  | Areas of highest risk: New features, Changed Feature, Complex features, Areas that were 'buggy' in the past, Mainstream functionality, Critical functionality, areas using new technology, areas with high complexity, and areas with low testability.
Coverage: | 2 Common Cases: all functions touched; common & critical tests executed
Quality: | Good
Ranking |  | Test Case, Charter, or Task | Estimate | Effort | Date |  |  | Critical Defects | Total Defects | Comments | OT | Total | Completed | Total A's | Completed A's
Priority | Order |  |  |  | Created | Start | Done
A | 1 | <charter 1> | 1 | [8 empty] | 1 | 0 | 1 | 0
A | 2 | <charter 2> | 1 | [8 empty] | 1 | 0 | 1 | 0
A | 3 | <charter 3> | 1 | [8 empty] | 1 | 0 | 1 | 0
A | 4 | <charter 4> | 1 | [8 empty] | 1 | 0 | 1 | 0
B | 1 | <charter 5> | 1 | [8 empty] | 1 | 0 | 0 | 0
B | 2 | <charter 6> | 1 | [8 empty] | 1 | 0 | 0 | 0
B | 3 | <charter 7> | 1 | [8 empty] | 1 | 0 | 0 | 0
B | 4 | <charter 8> | 1 | [8 empty] | 1 | 0 | 0 | 0
C | 1 | <charter 9> | 1 | [8 empty] | 1 | 0 | 0 | 0
C | 2 | <charter 10> | 1 | [8 empty] | 1 | 0 | 0 | 0
[8 empty] | 0 | 0 |  |  | 10 | 0 | 4 | 0
http://michaeldkelly.com/blog/2012/5/4/session-based-test-management.html

## Session Summary
Session | Date | Duration | Charter | Opportunity | Interuptions | Test | Defect | Setup | Defects | Issues
<Name> | 2014-03-11 | 2:00 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
|  | 2:00 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Column Definitions
SESSION = the title of the session report
This value is linked to the actual session report, which you can view for more information about the session.
DATE = the day the session started
DURATION = the approximate duration of the session
Duration is specified in terms of normal session units. Each session is worth about 90 minutes (or 3 pomodors or 25 minutes each) of uninterrupted tester attention.
CHARTER = total amount of on-charter work
The total amount of session work that was within the charter of each session. This value plus the Opportunity value should equal the total amount of session work associated with the corresponding coverage area. CHARTER + OPPORTUNITY = TOTAL
OPPORTUNITY = total amount of off-charter work
The amount of session work that was not within the charter of each session. The TBS breakdown for opportunity testing is not reported. All we know is that the work was off the subject of the specific charter. CHARTER + OPPORTUNITY = TOTAL
INTERUPTIONS = number of times distracted (phone, unscheduled meeting, impromptu off-charter discussion…)
TEST = amount of on-charter test design and execution
The amount of on-charter work that was devoted to searching for defects. The higher this value, the more time was spent by testers productively testing. TEST + DEFECT + SETUP = CHARTER.
DEFECT = amount of on-charter defect investigation and reporting that interrupted testing
The amount of on-charter work that was devoted to investigating and reporting defects. This work is only reported if it interrupts defect searching. Thus, the fewer problems there are, or the easier they are to investigate, the lower this value will be, and the more testing will get done. TEST + DEFECT + SETUP = CHARTER.
SETUP = amount of session setup work that interrupted testing
The amount of on-charter work that was devoted to anything other than bug searching or bug investigation and reporting. This work is only reported if it interrupts bug searching. Typically, this category includes gathering information for testing, setting up equipment, or filling out the session reports. Thus, the more organized the test process is, the lower this value will be, and the more testing will get done. Chronically high setup values probably indicate that the test project is still getting up to speed. TEST + BUG + SETUP = CHTR.
DEFECTS = total number of defectss found in sessions associated with this coverage area
The total number of defects reported to the test lead during the session. Not every defect reported to the test lead will be proper to report in the defect tracking system.
ISSUES = total number of issues found in sessions associated with this coverage area
The total number of issues reported in the session. Issues can be problems with the test process or questions about the product that are escalated to the test lead.

## Session Report
Session Report | <Name> | Environments | Testing Strategies | Tester | Duration
Charter |  | Dev1 | Functional Testing | Charles | Short
<Mission> |  | Dev2 | Functional Analysis |  | Medium
Areas |  | Test | Defect Regression |  | Long
|  | PR |  |  | Special
Environment |  | Demo
Strategy |  | Production
Start Date | 2014-03-11
Start Time | 15:00
End Time | 17:00
Tester
Test Breakdown
Duration
Test Design/Execution | 0%
Defect | 0%
Session Setup | 0%
% On Charter | 0%
% On Opportunity | 0%
Interuptions | 0
Data Files | <List>
<List>
Test Notes
Defect/OTDs | Description
1
8
Issues/OTDs | Description
Manager Debriefing
Past. What happened during the session?
Results. What was achieved during the session?
Obstacles. What got in the way of good testing?
Outlook. What still needs to be done?
Feelings. How does the tester feel about all this?
Tag your test notes to better identify topics: D - defect C - new charter ? - question A - automate DOC - document S - test setup T - testing I - investigate
http://www.satisfice.com/articles/sbtm.pdf

## Completed
Charters Completed
Area | Total A's | A's Completed | % Complete | Remaining A's
Area Name | 4 | 0 | 0% | 4
Total | 4 | 0 | 0% | 4

## Velocity
Charter Velocity
Day of Testing | Charters Created | Charters Executed | Remaining Charters
2014-03-11 | 10 | 9 | 30
2014-03-12 | 8 | 9 | 29
2014-03-13 | 12 | 9 | 32
2014-03-14 | 14 | 10 | 36
2014-03-15 | 11 | 11 | 36
2014-03-16 | 10 | 9 | 37
2014-03-17 | 8 | 9 | 36
2014-03-18 | 9 | 8 | 37
2014-03-19 | 5 | 9 | 33
2014-03-20 | 2 | 9 | 26
2014-03-21 | 6 | 9 | 23
2014-03-22
2014-03-23
2014-03-24
2014-03-25
2014-03-26
2014-03-27
2014-03-28
2014-03-29
2014-03-30
2014-03-31
2014-04-01
2014-04-02
2014-04-03
2014-04-04
2014-04-05
2014-04-06
2014-04-07
2014-04-08
2014-04-09
Formulas:
Day of Testing = [Day of Testing, row above]+1